## Sheet1
This sample timeline identifies typical components included in a recruitment plan and helps to keep the activities on track. It can be used to tailor any type of recruitment whether it be a classified service, professional or a management position. It is a tool that visually describes the steps involved in a recruitment effort. The tool works well when working with your hiring manager to describe each step and who is responsible; it gets their commitment to the process as well as identifies their tasks.
Hiring Process Timeline
| Projected |  | Notes | Who | Actual
Activity | Begin | Through |  |  | Begin | Through
Determine needed position | Day 1 |  |  | HR & Hiring Manager
Develop position description | Day 2 |  |  | HR & Hiring Manager
Determine Job Boards to be used | Day 2 |  |  | HR
Outreach/Networking/Employee Referral | Day 3 | Day 4 |  | HR
Application/Resume Review | Day 10 | Day 15 | Determines Viabilility | HR
Interview Question Development | Day 10 |  |  | HR & Hiring Manager
Determine Interview process and participants | Day 10
Schedule/Coordinate Interviews | Day 15 |  |  | HR
First Round Interviews | Day 20 |  |  | HR & Hiring Manager
Background/Reference Checks on Finalists | Day 25 |  | Requires 10 days | HR
Finalists for Review | Day 30 |  |  | HR
Final Interview for top 3 candidates | Day 35 | Day 40 |  | HR & Hiring Manager
Offer Position-Verbally | Day 45 |  | Allows for notice | Hiring Manager
Prepare offer lettter and packet | Day 46
Send Regrets to Remaining Applicants | Day 46 | Day 50 |  | HR
Determine start date | Day45 | Day 48
Prepare new hire documents and orientation | Day48 | Day 59
New Employee Starts | Day 60 |  |  | Candidate